## Sheet1
Sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Initial Understanding of requirements and set up | Environment Set up (Node JS, Postman, VS Code, Mongo DB, Git | All | Day 0: 4; Day 3: 2; Day 5: 1; Day 7: 1
| Architecture Diagram | All | Day 0: 4; Day 1: 2; Day 2: 1; Day 5: 2
| Learning and knowledge transfer of MERN stack | All | 4 |  |  | 2 | 1 | 1 |  | 1
| Learning and KT of React JS, MongoDB, Node JS | All | Day 0: 4; Day 6: 2
Remaining Effort |  |  | 16 | 14 | 13 | 9 | 8 | 4 | 2 | 0
Ideal Trend |  |  | 16 | 14.8571 | 13.7143 | 12.5714 | 11.4286 | 10.2857 | 9.1429 | 8
Sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Application Flow and Database Design | Class Diagram | Vinay | Day 0: 8; Day 1: 2; Day 3: 3; Day 6: 3
| Design Database Schema | Ramya | Day 0: 7; Day 2: 1; Day 3: 4; Day 5: 2
| Application flow | Javeed | Day 0: 6; Day 2: 2; Day 3: 3; Day 6: 1
| UI pages determinitation | All | 11 | 1 | 1 | 2 | 2 |  | 3 | 2
Remaining Effort |  |  | 32 | 29 | 25 | 13 | 11 | 9 | 2 | 0
Ideal Trend |  |  | 32 | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16
Sprint 3
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
API Creation, Wireframes and Database Design | Create login & signup API | Ramya | 8 | 1 | 1 | 2 |  | 1 | 3
| Create wireframes for Loginpage, Registerpage, Hoteloverview, Homepage, Bookdetails | Javeed, Vinay | 8 | 2 |  | 3 | 3 |  |  | 1
| Creating models for booking, room, user | Ramya | Day 0: 8; Day 2: 3; Day 4: 3; Day 6: 1
| Create login & signup Frontend | Javeed, Vinay | 8 | 2 | 1 |  | 2 | 3
Remaining Effort |  |  | 32 | 27 | 22 | 17 | 9 | 5 | 1 | 0
Ideal Trend |  |  | 32 | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16
Sprint 4
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Admin, Routing, API and Frontend code setup | Created Initial routing setup | Ramya | Day 0: 5; Day 1: 2; Day 2: 1; Day 4: 2
| Implement Landing page UI, Search UI | Javeed | Day 0: 8; Day 1: 3; Day 3: 3; Day 4: 2
| Implement customer profile details api | Ramya | Day 0: 5; Day 2: 3; Day 4: 2; Day 6: 1
| Implement Booking details api | Ramya | Day 0: 8; Day 1: 2; Day 3: 4; Day 5: 2
| Created Edit Booking api | Vinay | 8 |  | 1 |  | 1 | 3 |  | 2
| Creating Add room page in Admin | Vinay, Javeed | 5 | 2 |  | 1 |  | 1 |  | 1
Remaining Effort |  |  | 39 | 30 | 25 | 17 | 10 | 4 | 3 | 0
Ideal Trend |  |  | 39 | 36.2143 | 33.4286 | 30.6429 | 27.8571 | 25.0714 | 22.2857 | 19.5
Sprint 5
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Development front end and API | Adding Nav bar routes, and boilerplate navigation code | Vinay | 8 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| Integrating search rooms with backend | Ramya | 10 | 3 | 2 | 3 | 1 |  | 1
| Integrating My profile and Booking details with backend | Ramya | Day 0: 5; Day 4: 2; Day 6: 3
| Cancel Booking API, get all bookings by user API | Javeed | 7 |  | 1 | 1 | 1 | 3 |  | 1
| Peack pricing | Javeed | Day 0: 5; Day 2: 1; Day 4: 2; Day 7: 2
Remaining Effort |  |  | 35 | 31 | 26 | 21 | 13 | 9 | 4 | 0
Ideal Trend |  |  | 35 | 33.1579 | 31.3158 | 29.4737 | 27.6316 | 25.7895 | 23.9474 | 22.1053
Sprint 6
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Frontend, Backend Development and Integration | Admin Add Room | Ramya | Day 0: 4; Day 1: 2; Day 4: 2
| Peak Pricing Integration | Javeed | Day 0: 7; Day 1: 3; Day 3: 3; Day 7: 1
| Use Rewards Points Integration | Javeed | 10 |  | 3 | 2 | 3 |  | 1 | 1
| Adding Aminities | Ramya | 8 |  | 2 |  | 3 |  | 2 | 1
| Filtering Rooms | Ramya | Day 0: 4; Day 4: 1; Day 5: 3
| Booking functionality | Vinay | Day 0: 5; Day 2: 2; Day 4: 2; Day 6: 1
Remaining Effort |  |  | 38 | 33 | 26 | 21 | 10 | 7 | 3 | 0
Ideal Trend |  |  | 38 | 36.2143 | 33.4286 | 30.6429 | 27.8571 | 25.0714 | 22.2857 | 19.5
Sprint 7
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Deployment and Testing | Validations for Edit Booking, Cancel Booking functionality from customer side | Vinay, Ramya | Day 0: 6; Day 2: 1; Day 4: 2; Day 5: 3
| Deployment | Ramya | Day 0: 8; Day 5: 3; Day 6: 3; Day 7: 2
| Validation check throughout application | All | Day 0: 4; Day 2: 3; Day 4: 1
| Testing all flows and data | All | 6 |  | 2 |  | 1 | 1 | 2
| Merge Conflicts and integration issues | Ramya | Day 0: 5; Day 2: 1; Day 4: 1; Day 5: 3
Remaining Effort |  |  | 29 | 29 | 22 | 22 | 17 | 7 | 2 | 0
Ideal Trend |  |  | 29 | 36.2143 | 33.4286 | 30.6429 | 27.8571 | 25.0714 | 22.2857 | 19.5